## ProjectTeam
Name | GitHub Alias | Role/s
Simon Schaad | simu83 | dev
Michel Utz | SoullessStone | dev, technical lead
Sabine Zumstein | hummbaeri | dev, features lead
Dominique Halter | domihalter84 | dev, features lead
Alexander Nussbaum | nussa2 | dev, design lead
Kevin Suter | xonyne | dev, scrum master
Role name | Responsibilities
dev | implements, tests and reviews features
scrum master | guides through the scrum process plans the sprints removes impediments
technical lead | defines the package structure and the project setup defines coding guidelines (example classes) decides on new technology, libraries, maven plugins, db changes (if necessary)
layout lead | defines the base layout for the views
features lead | does an absolute priorization of the user stories in the product backlog defines what functionality the user stories should contain (via acceptance criteria) defines what will be done in the next sprint

## Product Backlog
ID | Story Name | Description | Priority (absolute) | Effort Plan Original | Effort Plan Remaining | Effort Actual | Status | Acceptance Criteria
1 | Patient overview - base data | Base data like address, city, phone | 999 | 16 | 0 | 16 | done | * show base data for patient
4 | Create meeting notes | Form for new meeting notes instance | 998 | 16 | 0 | 16 | done | * ability to enter free text notes
11 | Session Handling, DB, Navigation, Layout | Navigation between views, base layout | 997 | 16 | 0 | 16 | done | * ability to navigate between pages via menu
8 | Create prescription | Create a new prescription for a patient | 996 | 4 | 0 | 0 | done | * ability to prescribe a new medicament for a patient
16 | Task 12 - UML Domain Model | Adapt UML diagram according to code | 995 | 4 | 0 | 0 | done | * ability to search for name and/or birthdate
17 | Task 13 - State Pattern | Introduce state pattern | 994 | 20 | 0 | 0 | done
2 | Patient search | Allow to search for patients | 993 | 12 | 0 | 0 | done
3 | Meeting patient history | Show meeting history of patient | 992 | 16 | 0 | 0 | done
15 | Improve look & feel of UI (customer feedback) | Improve usability & menu | 991 | 6 | 0 | 0 | done
18 | Goldplatting | icons personsearch, link person->meeting, personsearch results format, personview dropdown weg, navigation person->doctor (inkl. Der meetings), mainlayout abstand der tiles grösser, annotion meeting notes mehr zeichen, aktuelle prescriptions auf patientenview, patientenview redesign (schmaler), annulieren persrciption | 990 | 0 | 0 | 0 | new
14 | Connect external systems | Connect medication DB and illness DB, icd-10 anbinden | 989 | 0 | 0 | 0 | new
21 | Patient in Session speichern | Der User kann einen Patienten auswählen. Dessen Infos werden dann in Person/Prescription/meeting angezeigt | 989 | 0 | 0 | 0 | new
20 | Diagnosis for Patient | Diagnosis(illness, date, note) | 986 | 0 | 0 | 0 | new
9 | Escalation | Escalation process for dangerous patients | 985 | 0 | 0 | 0 | new
12 | Search patient history | Search for patient history (meetings, diagnoses) | 500 | 0 | 0 | 0 | new
19 | Goldplatting optional | medikamentensuche, eine person ausgewählt->navigation ergibt wieder sinn | 980 | 0 | 0 | 0 | new
7 | Edit prescription | Edit a prescription | 500 | 0 | 0 | 0 | new
10 | Edit patient base data | Edit base data like address, phone etc. | 500 | 0 | 0 | 0 | new
13 | Printing functionality | Ability to print views | 500 | 0 | 0 | 0 | new

## Sprint Backlog
User Story ID | Sprint | Name | Comment | Components | Assignee | Reviewer | Priority | Planned effort | Remaining effort | Actual effort | Status (new, assigned, in progress, in review, done) | Due date
11 | 1 | Project and vaadin setup | has to be done first | UI | michel, kevin | alex | 1 - (high) | 8 |  |  | done | 2016-05-14
11 | 1 | Create base layout | has to be done first | UI | alex | all | 1 - (high) | 8 |  | 4 | done | 2016-05-14
1 | 1 | Create overview view |  | UI | simon | alex | 2 - (medium) | 6 |  |  | done | 2016-05-15
1 | 1 | Create patient model |  | Database | simon | domi | 2 - (medium) | 2 |  |  | done | 2016-05-22
1 | 1 | Create overview presenter |  | Controller | simon | alex | 2 - (medium) | 6 |  |  | done | 2016-05-22
14 | 1 | Create prescriptions tile |  | UI | domi | michel | 2 - (medium) | 2 |  |  | done | 2016-05-22
14 | 1 | Create prescriptions model |  | Database | domi | michel | 2 - (medium) | 1 |  |  | done | 2016-05-22
14 | 1 | Create prescriptions presenter |  | Controller | domi | michel | 2 - (medium) | 1 |  |  | done | 2016-05-22
1 | 1 | Add mock base data for patients |  | Database | domi | kevin | 2 - (medium) | 2 |  |  | done | 2016-05-22
11 | 1 | Create DB tables |  | DB | domi | kevin | 2 - (medium) | 2 |  |  | done | 2016-05-15
4 | 1 | Create meeting notes view |  | UI | sabine | kevin | 2 - (medium) | 6 |  | 4 | done | 2016-05-15
4 | 1 | Create meeting notes model |  | Database | sabine | kevin | 2 - (medium) | 2 |  | 4 | done | 2016-05-22
4 | 1 | Create meeting notes presenter |  | Controller | sabine | kevin | 2 - (medium) | 6 |  | 2 | done | 2016-05-22
3 | 2 | Make Prescriptions persistable |  | DB | alex | kevin | 2 - (medium) | 4 |  |  | done | 2016-05-29
3 | 2 | Read real patient data from database | Remove person inheritance | DB | simon | alex | 2 - (medium) | 6 |  |  | done | 2016-05-29
3 | 2 | Show meeting history in patient overview | Connect with meeting view | UI | sabine | michel | 2 - (medium) | 6 |  |  | done | 2016-05-29
2 | 2 | Person search view | Connect with patient overview | UI | michel | sabine | 2 - (medium) | 4 |  |  | done | 2016-05-29
2 | 2 | Person search controller |  | Controller | michel | sabine | 2 - (medium) | 5 |  |  | done | 2016-05-29
2 | 2 | Person search model |  | DB | sabine | michel | 2 - (medium) | 3 |  |  | done | 2016-05-29
15 | 2 | Improve look & feel of application |  | UI | domi | all | 2 - (medium) | 6 |  |  | done | 2016-05-29
17 | 2 | Indicate meeting states in GUI |  | UI | alex, simon | kevin | 1 - (high) | 10 |  |  | done | 2016-05-29
17 | 2 | Allow meeting to have different states |  | Model & Controller | kevin | simon, alex | 1 - (high) | 10 |  |  | done | 2016-05-29
16 | 2 | Adapt UML diagram | Only model layer | DB | alex, simon | all | 1 - (high) | 4 |  |  | done | 2016-05-29
18 | 3 | Code Inspection | FindBugs incl. Corrections | all | alex |  | 1 - (high) | 3 |  | 0 | assigned | 2016-06-14
14 | 3 | Create illness model | icd-10 style | DB | kevin |  | 2 - (medium) | 6 |  |  | assigned | 2016-06-14
14 | 3 | Show illnesses in GUI | incl. search for illnesses | UI | sabine |  | 2 - (medium) | 6 |  |  | assigned | 2016-06-14
14 | 3 | Connect or mock illness DB | mock it first | Controller | kevin |  | 2 - (medium) | 14 |  |  | assigned | 2016-06-14
21 | 3 | Patient in Session | incl. adaption of menu | all | simon |  | 1 - (high) | 10 |  | 0 | assigned | 2016-06-14
20 | 3 | Diagnosis for patient - model | date of diagnosis, illness-id, (notes) | DB | alex |  | 2 - (medium) | 4 |  |  | assigned | 2016-06-14
20 | 3 | Diagnosis for patient - controller |  | Controller | alex |  | 2 - (medium) | 4 |  |  | assigned | 2016-06-14
20 | 3 | Diagnosis for patient - view | Button in wiki, adapt person view, popup to enter notes after clicking button | UI | michel |  | 2 - (medium) | 6 |  |  | assigned | 2016-06-14
9 | 3 | Escalation - button, Patient changes state | Dropdown in GUI, enum on DB | UI | domi |  | 2 - (medium) | 6 |  |  | assigned | 2016-06-14
9 | 3 | Escalation - send mail to VGJ1 |  | Controller | domi, simon |  | 2 - (medium) | 8 |  |  | assigned | 2016-06-14
18 | 3 | Rework person search view | Insert Grid Layout | UI | michel |  | 2 - (medium) | 2 |  |  | done | 2016-06-14
18 | 3 | Insert icons, shadows, margins |  | UI | sabine |  | 2 - (medium) | 3 |  |  | assigned | 2016-06-14
18 | 3 | Link meeting tile to meeting details |  | UI | domi |  | 2 - (medium) | 2 |  |  | done | 2016-06-14
Total | [7 empty] | 70

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180