## ProjectTeam
Name | GitHub Alias | Role/s
Simon Schaad | simu83 | dev
Michel Utz | SoullessStone | dev, technical lead
Sabine Zumstein | hummbaeri | dev, features lead
Dominique Halter | domihalter84 | dev, features lead
Alexander Nussbaum | nussa2 | dev, design lead
Kevin Suter | xonyne | dev, scrum master
Role name | Responsibilities
dev | implements, tests and reviews features
scrum master | guides through the scrum process plans the sprints removes impediments
technical lead | defines the package structure and the project setup defines coding guidelines (example classes) decides on new technology, libraries, maven plugins, db changes (if necessary)
layout lead | defines the base layout for the views
features lead | does an absolute priorization of the user stories in the product backlog defines what functionality the user stories should contain (via acceptance criteria) defines what will be done in the next sprint

## Product Backlog
ID | Story Name | Description | Priority (absolute) | Effort Plan Original | Effort Plan Remaining | Effort Actual | Status | Acceptance Criteria
1 | Patient overview - base data | Base data like address, city, phone | 999 | 16 | 0 | 0 | in progress | * show base data for patient
4 | Create meeting notes | Form for new meeting notes instance | 998 | 16 | 0 | 0 | in progress | * ability to enter free text notes
11 | Session Handling, DB, Navigation, Layout | Navigation between views, base layout | 997 | 16 | 0 | 0 | in progress | * ability to navigate between pages via menu
8 | Create prescription | Create a new prescription for a patient | 996 | 4 | 0 | 0 | in progress | * ability to prescribe a new medicament for a patient
2 | Patient search | Create search bar and menu | 1 | 0 | 0 | 0 | new
3 | Patient history | Show illness history of patient | 1 | 0 | 0 | 0 | new
5 | Create wiki entries | Create a new wiki article | 1 | 0 | 0 | 0 | new
6 | Show wiki entries | Show wiki article attached to an illness | 1 | 0 | 0 | 0 | new
7 | Edit prescription | Edit a prescription | 1 | 0 | 0 | 0 | new
9 | Escalation | Escalation process for dangerous patients | 1 | 0 | 0 | 0 | new
10 | Edit patient base data | Edit base data like address, phone etc. | 1 | 0 | 0 | 0 | new
12 | Search patient history | Search for patient history (meetings, diagnoses) | 1 | 0 | 0 | 0 | new
13 | Printing functionality | Ability to print views | 1 | 0 | 0 | 0 | new
14 | Connect external systems | Connect medication DB and illness DB | 1 | 0 | 0 | 0 | new
15 | Responsive Design | Enable support for mobile clients | 1 | 0 | 0 | 0 | new

## Sprint Backlog
User Story ID | Sprint | Name | Comment | Components | Assignee | Reviewer | Priority | Planned effort | Remaining effort | Actual effort | Status (new, assigned, in progress, in review, done) | Due date
11 | 1 | Project and vaadin setup | has to be done first | UI | michel, kevin | alex | 1 - (high) | 8 |  |  | in progress | 2016-05-14
11 | 1 | Create base layout | has to be done first | UI | alex | all | 1 - (high) | 8 |  |  | in progress | 2016-05-14
1 | 1 | Create overview view |  | UI | simon | alex | 2 - (medium) | 6 |  |  | in progress | 2016-05-15
1 | 1 | Create patient model |  | Database | simon | domi | 2 - (medium) | 2 |  |  | in progress | 2016-05-22
1 | 1 | Create overview presenter |  | Controller | simon | alex | 2 - (medium) | 6 |  |  | in progress | 2016-05-22
14 | 1 | Create prescriptions tile |  | UI | domi | michel | 2 - (medium) | 2 |  |  | in progress | 2016-05-22
14 | 1 | Create prescriptions model |  | Database | domi | michel | 2 - (medium) | 1 |  |  | in progress | 2016-05-22
14 | 1 | Create prescriptions presenter |  | Controller | domi | michel | 2 - (medium) | 1 |  |  | in progress | 2016-05-22
1 | 1 | Add mock base data for patients |  | Database | domi | kevin | 2 - (medium) | 2 |  |  | in progress | 2016-05-22
11 | 1 | Create DB tables |  | DB | domi | kevin | 2 - (medium) | 2 |  |  | in progress | 2016-05-15
4 | 1 | Create meeting notes view |  | UI | sabine | kevin | 2 - (medium) | 6 |  |  | in progress | 2016-05-15
4 | 1 | Create meeting notes model |  | Database | sabine | kevin | 2 - (medium) | 2 |  |  | in progress | 2016-05-22
4 | 1 | Create meeting notes presenter |  | Controller | sabine | kevin | 2 - (medium) | 6 |  |  | in progress | 2016-05-22
Total | [7 empty] | 52

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180